## AI Dashboard Tracker
Completed | Section | Task | Estimated Hours | GitHub Action / Commit | LinkedIn Content Idea
Planning
| Planning | Define project scope and modules | 2 |  | LinkedIn post: Learning how to structure scalable AI-enabled web applications
| Planning | Create project requirements document | 2
| Planning | Choose tech stack and architecture | 2
| Planning | Create GitHub repositories (frontend/backend) | 1 | Initial repo setup commit
| Planning | Setup README structure | 1 | README initial setup
Frontend Setup
| Frontend Setup | Create React + Vite + TypeScript app | 1 | Frontend initial setup
| Frontend Setup | Install Tailwind CSS | 1 | Tailwind setup
| Frontend Setup | Setup ESLint and Prettier | 1 | Linting setup
| Frontend Setup | Configure folder structure | 2 | Folder architecture setup | Post: Organizing scalable React applications
| Frontend Setup | Setup routing | 1 | React Router setup
| Frontend Setup | Setup environment variables | 0.5 | Env configuration
| Frontend Setup | Setup state management | 2 | Redux/Zustand setup
| Frontend Setup | Setup API layer | 2 | Axios/API services setup
Backend Setup
| Backend Setup | Create Node.js + Express + TypeScript app | 2 | Backend initial setup
| Backend Setup | Setup Prisma ORM | 2 | Prisma configuration
| Backend Setup | Setup PostgreSQL database | 2 | Database connection setup
| Backend Setup | Setup environment configuration | 1 | Backend env setup
| Backend Setup | Setup logging middleware | 1 | Logger setup
| Backend Setup | Setup error handling middleware | 1 | Error handling setup
Authentication
| Authentication | Create user model | 2 | User schema/model
| Authentication | Implement signup API | 3 | Signup API implementation
| Authentication | Implement login API | 3 | Login API implementation
| Authentication | Implement JWT token generation | 2 | JWT setup | Post: JWT authentication learnings
| Authentication | Implement refresh token flow | 4 | Refresh token implementation | Post: Solving token refresh edge cases
| Authentication | Implement logout API | 1 | Logout functionality
| Authentication | Create protected routes | 2 | Protected route implementation
| Authentication | Add forgot password flow | 4 | Password reset feature
| Authentication | Frontend login/signup pages | 4 | Authentication UI
| Authentication | Form validation using Zod | 2 | Validation setup
Dashboard UI
| Dashboard UI | Create responsive sidebar | 3 | Sidebar component
| Dashboard UI | Create top navbar | 2 | Navbar component
| Dashboard UI | Create dashboard cards | 3 | Reusable card components
| Dashboard UI | Create reusable modal component | 2 | Modal component
| Dashboard UI | Create reusable table component | 4 | Table component
| Dashboard UI | Add dark/light theme | 3 | Theme implementation | Post: Theme switching in React applications
| Dashboard UI | Responsive mobile optimization | 4 | Responsive UI updates
User Management
| User Management | Create user list page | 3 | User management page
| User Management | Implement add user | 2 | Add user feature
| User Management | Implement edit user | 2 | Edit user feature
| User Management | Implement delete user | 1 | Delete user feature
| User Management | Implement pagination | 2 | Pagination feature
| User Management | Implement search/filter | 3 | Search and filtering | Post: Building reusable filtering systems
Analytics
| Analytics | Setup Recharts | 1 | Charts library setup
| Analytics | Create revenue analytics chart | 3 | Revenue chart
| Analytics | Create user activity chart | 3 | User analytics chart
| Analytics | Create dashboard metrics section | 2 | Metrics cards
| Analytics | Implement date range filtering | 3 | Date filtering feature
| Analytics | Optimize chart rendering | 2 | Chart optimization | Post: Improving dashboard rendering performance
AI Integration
| AI Integration | Setup Gemini/OpenAI API | 2 | AI API setup
| AI Integration | Create AI assistant backend route | 3 | AI route implementation
| AI Integration | Create AI chat UI | 4 | AI chat component
| AI Integration | Implement AI response streaming | 4 | Streaming response handling | Post: Handling streaming AI responses in React
| AI Integration | Create AI report generation feature | 5 | AI report feature
| AI Integration | Implement AI-based search | 5 | AI smart search feature | Post: Exploring AI-powered dashboard search
| AI Integration | Optimize prompts | 3 | Prompt improvements
| AI Integration | Handle AI error states | 2 | AI error handling
Notifications
| Notifications | Setup toast notifications | 1 | Toast notification setup
| Notifications | Create notification center UI | 3 | Notification UI
| Notifications | Unread notification handling | 2 | Unread count implementation
File Upload
| File Upload | Setup Multer middleware | 2 | File upload backend setup
| File Upload | Setup Cloudinary | 2 | Cloudinary integration
| File Upload | Profile image upload feature | 3 | Profile upload feature
Performance Optimization
| Performance Optimization | Implement lazy loading | 2 | Lazy loading optimization
| Performance Optimization | Implement code splitting | 2 | Code splitting setup
| Performance Optimization | Optimize React re-renders | 4 | Memoization optimization | Post: React re-render optimization learnings
| Performance Optimization | Optimize API caching | 3 | Caching improvements
| Performance Optimization | Optimize large table rendering | 3 | Table virtualization
Testing
| Testing | Setup Jest | 1 | Testing setup
| Testing | Write auth API tests | 3 | Auth tests
| Testing | Write frontend component tests | 4 | Frontend tests
Deployment
| Deployment | Deploy frontend to Vercel | 2 | Frontend deployment | Post: First deployment learnings
| Deployment | Deploy backend to Render/Railway | 2 | Backend deployment
| Deployment | Deploy PostgreSQL database | 1 | Database deployment
| Deployment | Setup environment variables | 1 | Production env setup
| Deployment | Production bug fixing | 4 | Production fixes
Documentation
| Documentation | Write setup instructions | 2 | README improvements
| Documentation | Add screenshots and GIFs | 2 | Project media upload
| Documentation | Document APIs | 3 | API documentation
| Documentation | Write project architecture explanation | 3 | Architecture documentation | Post: Architecture learnings from building dashboard
LinkedIn/GitHub
| LinkedIn/GitHub | Push commits consistently | Ongoing | Daily/feature-based commits
| LinkedIn/GitHub | Write one technical LinkedIn post weekly | Ongoing |  | Technical learning/optimization/AI integration posts
| LinkedIn/GitHub | Add screenshots to GitHub README | 2 | README screenshots
| LinkedIn/GitHub | Record small demo videos | 2 | Demo recordings